## Neighbors Task Board
ID | Task | Description | Start Date | Due Date | Department | Assigned to | Days to Complete
Proj1 | Plan Front-End functionality and Requrements | Design the Front-end functionality and the Languages and Capabilities needed to Code it into the websites | 2020-10-12 | 2020-12-07 | Technology | Akshat | 56
Proj3 | Backend | Choose Data hosting service based on developers' skill levels and budget | 2020-12-07 | 2020-12-21 | Technology | Connie | 14
Proj4 | Authentication | Create client to database authentication by using a token of choice | 2020-12-21 | 2021-01-10 | Technology | Sunita | 20
Proj10 | Budgeting | Compile the results of budget calculations from other planning modules | 2021-01-10 | 2021-01-18 | Accounting | Ram | 8
Proj18 | Create Logo and color scheme for Interface | Develop a logo and colors for the website | 2020-10-27 | 2020-11-24 | Design | Ritesh | 28
Proj22 | Create Profile page feature | Set different planned features for lenders and renters | 2021-01-18 | 2021-03-01 | Technology | Advait | 42
Proj21 | Add Login Page | Different login page for different login methods | 2021-01-18 | 2021-03-01 | Technology | Preston | 42
Proj11 | Security Configuration | Study how to set up server authentication | 2021-03-01 | 2021-03-15 | Technology | Akshat | 14
Proj13 | Maps Functionality Development | Develop Google maps integration | 2021-03-15 | 2021-04-12 | Technology | Connie | 28
Proj9 | Payment Services | Explore options for payments and budget for licensing to different payment authentication services | 2021-03-15 | 2021-04-12 | Accounting | Sunita | 28
Proj14 | Add functionality to post Items | Create functionality to be able to post items for rental | 2021-04-12 | 2021-05-10 | Technology | Ram | 28
Proj15 | Add ability to rent items | Create functionality to be able to pay and schedule items for rental | 2021-05-10 | 2021-06-07 | Technology | Ritesh | 28
Proj16 | Develop Messaging Functionality | Messaging functionality between renters and lenders | 2021-05-10 | 2021-06-21 | Technology | Advait | 42
Proj17 | Add search and filter functionality | Search and filter for items by distance, category | 2021-05-17 | 2021-06-21 | Technology | Preston | 35
Proj5 | Hosting Services | Choose a hosting service for the number of users and budget depending on speed requirements and customer load | 2021-05-24 | 2021-05-31 | Technology | Akshat | 7
Proj6 | Sub-task | describe your task... |  | 2020-11-05 | Design | Awareness | 44140
Proj7 | Sub-task | describe your task... |  | 2020-10-18 | Sales | Retention | 44122
Proj20 | Add damage reporting and complaints feature |  | 2021-05-31 | 2021-06-07 | Legal | Connie | 7
Proj12 | Integration Testing | Finish all full unit testing and integration testing | 2021-06-21 | 2021-07-05 | Technology | Sunita | 14
Proj19 | Take out commision from rental fees | Later on, we take a part of the rental fee as revenue | 2021-06-07 | 2021-06-21 | Marketing | Ram | 14
Proj25 | Implement feedback and bug reporting services | Create text boxes to submit complaints | 2021-05-31 | 2021-06-14 | Legal | Ritesh | 14
Proj23 | Create mobile app | Lead team of developers to create the mobile app | 2020-11-24 | 2021-02-16 | Technology | Advait | 84